## Hoja1
Name | Martha Jiménez | Date | 2013-06-24
Chairperson |  | Location | Infotec
Meeting Date | 2013-06-17
Start Time | 17:38 | End Time | 19:36
Subject/Purpose | Junta Semanal no. 3
Attendees
Name |  | Role
Carlos Ramos (CIRI) |  | Team Leader
José Jiménez (JRJN) |  | Team Member
Martha Jiménez (MEJS) |  | Team Member
Victor Lorenzana (VHLG) |  | Coach
Adriana González |  | Mentor Coach
Times (min.)
Plan | Start | Stop | Topics | Discussion Leader
| 17:38 | 17:38 | Meeting roles | CIRI
| 17:38 | 17:38 | Meeting agenda | CIRI
| 17:38 | 17:41 | Manager's Report | CIRI
| 17:41 | 18:23 | Role Report | CIRI
| 18:23 | 19:06 | Proyect Status | CIRI
| 19:06 | 19:22 | Goal and Risk Reports | CIRI
| 19:22 | 19:28 | Next Week Plans | CIRI
| 19:28 | 19:28 | Meeting Wrap-up | CIRI
| 19:28 | 19:28 | Meeting Conclusion | CIRI
| 19:28 | 19:36 | Meeting Report | CIRI
What |  |  | Who | When
Reunión despues de la reunión semanal de revisión para ver cu, escenarios y casos de prueba |  |  | Equipo | 2013-06-25
Reunión después de la reunión semanal de revisión para ver tamaños actuales. |  |  | Jose y Carlos | 2013-06-25
Agregar en la tabla la diferencia de plan-actual de horas directas y valor ganado |  |  | Carlos | Siguiente reporte
Respaldar datos de dashboard |  |  | Martha | Semanalmente
Agregar al reporte, la subestimación de tiempo representado en recursos y horas necesarios para alcanzar la fehca planeada |  |  | Martha | Siguiente reporte
El miércoles 26 a las 12:30 a 13:00 no reuniremos con Mr. Coach para calcular los tiempos de subestimación |  |  | Equipo y coach | 2013-06-26