## Hoja1
Name | Carlos Ramos | Date | 2013-07-04
Chairperson |  | Location | Infotec
Meeting Date | 2013-07-04
Start Time | 11:25 | End Time | 12:39
Subject/Purpose | Junta Gerencial no. 2
Attendees
Name |  | Role
Carlos Ramos (CIRI) |  | Team Leader
Javier Solís Gonzalez (JSG) |  | Manager
Victor Lorenzana (VHLG) |  | Coach
Thania Mares |  | AP
Times (min.)
Plan | Start | Stop | Topics | Discussion Leader
| 11:25 | 11:30 | Meeting introduction | CIRI
| 11:30 | 11:45 | Project status | CIRI
| 12:09 | 12:29 | Risk and actins | CIRI
| 12:29 | 12:30 | Other agenda items | JSG
| 12:30 | 12:31 | Meeting Conclusion | CIRI
What |  |  | Who | When
Platicar con el equipo para buscar cubrir los tiempos planeados |  |  | Equipo y JSG | La próxima semana
Revisará cómo llevamos los procesos para buscar aligerarlos |  |  | VHLG | La próxima semana
Realizar lista de candidatos para tomar el curso de psp |  |  | VHLG | La próxima semana
Gerencia no ha definido si se incrementará el tamaño del equipo para el próximo ciclo