## Hoja1
Name | José Jiménez | Date | 2013-07-15
Chairperson |  | Location | Infotec
Meeting Date | 2013-07-15
Start Time | 17:15 | End Time:
Subject/Purpose | Junta Semanal no. 6
Attendees
Name |  | Role
Carlos Ramos |  | Team Leader
José Jiménez |  | Team Member
Martha Jiménez |  | Team Member
Victor Lorenzana |  | Coach
Times (min.)
Plan | Start | Stop | Topics | Discussion Leader
| 17:15 | 17:15 | Meeting roles | CIRI
| 17:15 | 17:15 | Meeting agenda | CIRI
| 17:16 | 17:54 | Manager's Report | CIRI
| 17:54 | 18:10 | Role Report | CIRI
| 18:10 | 19:01 | Proyect Status | CIRI
| 19:01 | 19:20 | Goal and Risk Reports | CIRI
| 19:20 | 19:20 | Next Week Plans | CIRI
| 19:20 | 19:20 | Meeting Wrap-up | CIRI
| 19:21 | 19:24 | Meeting Conclusion | CIRI
|  |  | Meeting Report | CIRI
What |  |  | Who | When
Agregar al checklist de revisión de código personal, el punto de revisión: Quitar comentarios de debug. Martha revisará esta semana su realización |  |  | Equipo | Esta semana
Agregar, al plan, las tareas necesarias para cubrir los puntos que se marcan como observaciones por parte del Administrador de pruebas, en reporte de esta semana.CIRI se encargará de revisar su realización. |  |  | Equipo | Miércoles de esta semana y en adelante
Enviar el promedio de horas y fecha pronosticada antes de las 12 hrs. de cada lunes. |  |  | Equipo | En adelante
Registrar todos los tiempos consumidos en la semana. Incluidas horas de reuniones, comidas, recreos, etc. |  |  | Equipo | En adelante