## Hoja1
Name | José Jiménez | Date | 2013-07-10
Chairperson |  | Location | Infotec
Meeting Date | 2013-07-10
Start Time | 12:16 | End Time | 18:18
Subject/Purpose | Junta Semanal no. 5
Attendees
Name |  | Role
Carlos Ramos |  | Team Leader
José Jiménez |  | Team Member
Martha Jiménez |  | Team Member
Victor Lorenzana |  | Coach
Adriana González |  | Mentor Coach
Times (min.)
Plan | Start | Stop | Topics | Discussion Leader
| 5:12 | 5:13 | Meeting roles | CIRI
| 5:13 | 5:13 | Meeting agenda | CIRI
| 5:13 | 5:16 | Manager's Report | CIRI
| 5:16 | 5:38 | Role Report | CIRI
| 5:38 | 5:49 | Proyect Status | CIRI
| 5:49 | 6:04 | Goal and Risk Reports | CIRI
| 6:04 | 6:08 | Next Week Plans | CIRI
| 6:10 | 6:12 | Meeting Wrap-up | CIRI
| 6:12 | 6:16 | Meeting Conclusion | CIRI
| 6:16 | 6:18 | Meeting Report | CIRI
What |  |  | Who | When
Se acepta la eliminación de la tarea para contar con VNC para el uso del Dashboard. Y se agrega como riesgo bajo responsabilidad de Martha |  |  | Todos | Esta semana
Los planes personales se respaldarán y enviarán por correo electrónico a Martha, para que a su vez los haga llegar a Víctor |  |  | Todos | En adelante
Cuando se modifique la ontología se deberan cargar a subversion los cambios hechos en las clases generadas |  |  | Todos | En adelante
Documentar las diferencias entre las pantallas de estados y períodos y considerarlas para un estándar |  |  | CIRI | Esta semana
Sustituir la gráfica utilizada en la presentación para Valor ganado acumulado que realizamos en Excel, por la que proporciona Dashboard |  |  | Todos | Esta semana