## Hoja1
Name | Carlos Ramos | Date | 2013-06-19
Chairperson |  | Location | Infotec
Meeting Date | 2013-06-19
Start Time | 11:50 | End Time | 12:10
Subject/Purpose | Junta Gerencial no. 1
Attendees
Name |  | Role
Carlos Ramos (CIRI) |  | Team Leader
Javier Solís Gonzalez (JSG) |  | Manager
Victor Lorenzana (VHLG) |  | Coach
Adriana González |  | Mentor Coach
Times (min.)
Plan | Start | Stop | Topics | Discussion Leader
| 11:50 | 11:58 | Meeting introduction | CIRI
| 11:58 | 12:01 | Project status | CIRI
| 12:01 | 12:03 | Risk and actins | CIRI
| 12:03 | 12:03 | Other agenda items | JSG
| 12:03 | 12:05 | Meeting Conclusion | CIRI
What |  |  | Who | When
Reforzar el compromiso de cumplir con las task hours semanales |  |  | Equipo | Cada semana
Reportar el status de los módulos trabajados en la quincena |  |  | CIRI | Cada junta gerencial
Reportar el status de los módulos trabajados en la semana |  |  | Equipo | Cada junta semanal