## GOAL
Name |  | Date
Project |  | Launch/Phase
| Measures |  | Tracking | Frecuency
Goal | Goal | Actual | Responsibility
Completar las funcionalidades proporcionadas por el cliente en su documento | 100% |  | CIRI | Semanal
Terminar el primer ciclo del proyecto en octubre | 2013-10-31 |  | MEJS | Semanal
Proveer oportunamente la información del proyecto acordada con el administrador del proyecto | 90% |  | CIRI | Semanal
Generar pips para el proceso de desarrollo de software | 1 por integrante |  | JRJN | Semanal
Recopilar metricas correctas de la ejecución completa de los procesos | 100% |  | JRJN | Semanal
Defectos mayores entregados al area de pruebas | <= 1 Def/Kloc |  | JRJN | Semanal

## ROLE
Name |  | Date
Project |  | Launch/Phase
Team Member Roles |  | Requirements | Design | Implementation | Integration and Test
Official Team Leader | CIRI
JRJN
Customer Interface | CIRI
Manager | JRJN
Design Manager | JRJN
MEJS
Implementation | MEJS
Manager | JRJN
Planning Manager | MEJS
JRJN
Process Manager | JRJN
MEJS
Quality Manager | JRJN
MEJS
Support Manager | MEJS
CIRI
Test Manager | CIRI
MEJS
P
A
P
A
P
A
P
A
P
A
P
A
P
A
P
A

## ITL Riesgos
Name |  |  | Date
Project |  |  | Launch/Phase
No. | Description | Date | Personal/Team | Risk/Issue | Impact | Likelihood | Owner | Follow-up Date | Resolved Date
No es posible estimar el requerimiento Acuerdo RAE (Acciones) debido a que desconocemos su definición. En concecuencia no entra en el plan calendario

## PIP
Name
E-mail
Project
Organization
Date | PIP Number | PIP Title | Improvement Description | Priority | Launch/Phase | Process Elements Impacted | Improvement Benefits description | Improved Quality | Reduced Cycle Time | Reduced Risk

## Minuta Junta 1
Name | Carlos Ramos Incháustegui | Date | 2013-05-27
Chairperson | Victor Lorenzana | Location | Infotec México
Meeting Date | 2013-05-27
Start Time | 10:49 | End Time | 12:31
Subject/Purpose | Lanzamiento Junta 1: Revisar con gerencia las metas y los objetivos del producto con el equipo
Attendees
Name |  | Role
Victor Hernández |  | Marketing
Javier Solís |  | Senior Managment
Carlos Rammos |  | Team Leader
José Jiménez |  | Team Member
Martha Jiménez |  | Team Member
Victor Lorenzana |  | Coach
Adriana González |  | Mentor Coach
Times (min.)
Plan | Start | Stop | Topics | Discussion Leader
| 10.49 | 11.04 | TSP and Launch Overview Meetig Role Assignments | Coach
| 11.05 | 11:25 | Project Goals | Senior Mgmt
| 11:26 | 11:32 | Goal Questions | Coach
| 11:34 | 11:54 | Product Objectives | Marketing mgmt
| 11:55 | 12:03 | Product Questions | Coach
| 12:11 | 12:31 | Launch Meeting Documentation | Coach
What | Who | When
Primer semana de octubre se define si terminamos el proyecto para diciembre. En caso afirmativo piloteamos en noviembre y sacamos el producto en diciembre al mercado interno. | Carlos Ramos | 2013-05-29
Incluir un plan de comunicación con Planeación estratégica en el plan calendario | Carlos Ramos | 29/02/2013
Acordar cómo y cuando se involucrará el area de pruebas en el plan calendario | Carlos Ramos | 2013-05-29
Enviar documento de presentación | Javier Solís | 2013-05-27
Enviar presentación de power point | Victor Hernández | 2013-05-27

## Minuta Junta 2
Name |  | Date
Chairperson |  | Location
Meeting Date
Start Time |  | End Time
Subject/Purpose
Attendees
Name |  | Role
Times (min.)
Plan | Start | Stop | Topics | Discussion Leader
| 13:22 | 13:38 | Meeting roles
| 13:39 | 13:42 | Meeting overview
| 15:24 | 15:26 | Meeting overview
What | Who | When

## Minuta Kunta 3
Name | José Jiménez | Date | 2013-05-27
Chairperson | Víctor Lorenzana | Location | Infotec México
Meeting Date | 2013-05-27
Start Time | 13:22 | End Time | 19:37
Subject/Purpose | Lanzamiento Junta 2.- Fijar metas y establecer roles
Attendees
Name |  | Role
Carlos Ramos |  | Team Leader
José Jiménez |  | Team Member
Martha Jiménez |  | Team Member
Victor Lorenzana |  | Coach
Adriana González |  | Mentor Coach
Times (min.)
Plan | Start | Stop | Topics | Discussion Leader
| 13:22 | 13:38 | Meeting roles | Coach
| 13:39 | 13:42 | Meeting overview | Coach
| 15:24 | 15:26 | Meeting overview | Coach
| 15:28 | 16:53 | Review Managment's Stated Goals | Lider
| 17:06 | 17:20 | Review Managment's Stated Goals | Lider
| 17:21 | 17:38 | Implied Goals | Lider
| 17:38 | 18:29 | Team Goals | Lider
| 18:41 | 18:45 | Team Goals | Lider
| 18:46 | 19:12 | Team Role Selection | Coach
| 19:14 | 19:23 | Team Role Selection | Coach
| 19:23 | 19:29 | Goal Tracking | Coach
| 19:29 | 19:37 | Launch Meeting Documentation | Coach
What | Who | When
Generar una actividad al inicio del proyecto para acordar la información a proporcionar al AP. | Carlos Ramos | Junta 4
Proponer la adquisición del módulo de gráficas de Gantt de Process Dashboard | Carlos Ramos | 2013-05-28

## Minuta
Name |  | Date
Chairperson |  | Location
Meeting Date
Start Time |  | End Time
Subject/Purpose
Attendees
Name |  | Role
Times (min.)
Plan | Start | Stop | Topics | Discussion Leader
What | Who | When